## Project Plan and Gantt
Project Name | Quản lý thư viện
Project Manager | Hồ Quốc Bình
Project Deliverable | 17/10/2016
Scope Statement:
Start Date | 2016-09-21
End Date | 2016-10-14
Overall Progress | 25%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Team | 2016-09-19 | 2016-09-20 | 1 | Complete
Agree on objectives | Team | 2016-09-19 | 2016-09-20 | 1 | Complete
Detailed Reqs. | Team | 2016-09-20 | 2016-09-26 | 6 | Complete
SQL Server Database | Quốc Bình | 2016-09-27 | 2016-09-28 | 1 | Complete
UI Java | Quốc Bình | 2016-09-28 | 2016-10-02 | 4 | Inprogress
Sign-in/Sign-up function | Hoàng Huân | 2016-09-29 | 2016-10-01 | 2 | Complete
Search by Name, Address | Hoàng Huân | 2016-10-02 | 2016-10-04 | 2 | Inprogress
JDBC/Connect SQL DB | Quốc Bình | 2016-09-28 | 2016-10-01 | 3 | Inprogress
Test WebService on Sever | Hoàng Huân | 2016-10-05 | 2016-10-05 | 0 | Not started
UI Client | Hoàng Huân | 2016-09-29 | 2016-10-01 | 2 | Inprogress
Insert/Update/Query | Quốc Bình | 2016-10-07 | 2016-10-08 | 1 | Not started
Testing | Hoàng Huân | 2016-10-09 | 2016-10-09 | 0 | Not started
Dev. Complete | Team | 2016-10-09 | 2016-10-10 | 1 | Not started
UI Updates | Hoàng Huân | 2016-10-11 | 2016-10-13 | 2 | Not started
Last Testing | Team | 2016-10-12 | 2016-10-13 | 1 | Not started
Launch |  | 2016-10-14 | 2016-10-14 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Lê Khánh | Team Leader, Developer | 1. Make the plan of the project. 2. Assign task for your member. 3. Design GUI/database. 4. Code. 5. Write document | kanelorange@gmail.com
Trần Minh Trung | Project Manager, Developer | 1. Design GUI/database. 2. Code. 3. Test 4. Analysis & design the system. | minhtrungdhth10e@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team