## Sheet1
Detailed Plan from 27/9 to 8/10
Responsible | Tasks | Start - End | Status
Hoàng Huân | Create Login UI | 2016-09-30 | Complete
| Add Login function | 2016-10-01 | Complete
| Update Login function: Set Username, Password | 2016-10-01 | Complete
| Update Login UI: Button "Click to Login" | 2016-10-02 | Complete
| Search by Name, Address function | 02/10 - 7/10 | Delayed
Quốc Bình